## Company Summary
Northgate Interiors Ltd: CVR at 30 September 2026
Job no. | Job | Forecast final value | Forecast final cost | Forecast margin | Margin % | Last month % | Movement (pp) | Over / (under) measure | Cash outstanding | RAG
J101 | Station Road flats | 488750 | 424895 | 63855 | 13.06% | 13.63% | -0.57 | 4550 | 50480 | Amber
J102 | Riverside school extension | 263100 | 280700 | -17600 | -6.69% | 2.48% | -9.17 | 5600 | 29550 | Red
J103 | Mill Lane offices fit-out | 152000 | 124750 | 27250 | 17.93% | 15% | 2.93 | 3000 | 34700 | Amber

## CVR J101
J101 Station Road flats: September 2026
| This month | Last month | Movement
Internal valuation | 273750 | 224000 | 49750
Forecast final value | 488750 | 489000 | -250
Forecast final cost | 424895 | 422350 | 2545
Forecast margin | 63855 | 66650 | -2795
Why the margin moved | £
Forecast final measure | 0
Recognised change | 3950
Deductions / contras | -4200
Own labour | -595
Labour-only subs | -3650
Materials | 8000
Plant & access | 0
Sub-subcontract | -200
Site overheads | -6100
Check | Result
1. Value and cost entered for this month | OK
2. Accruals carried from an earlier month | Confirm 1 carried accrual(s).
3. Recognition overridden without a reason | OK
4. Cost to complete is just budget less cost to date | OK
5. Negative cost to complete | OK
6. Big margin move, or well above tender | OK
7. Main contractor valuing below our application, three months running | 8.6% below our application this month.

## CVR J102
J102 Riverside school extension: September 2026
| This month | Last month | Movement
Internal valuation | 168100 | 130100 | 38000
Forecast final value | 263100 | 265600 | -2500
Forecast final cost | 280700 | 259000 | 21700
Forecast margin | -17600 | 6600 | -24200
Why the margin moved | £
Forecast final measure | 0
Recognised change | 0
Deductions / contras | -2500
Own labour | -15800
Labour-only subs | -5000
Materials | -1000
Plant & access | 0
Sub-subcontract | 0
Site overheads | 100
Check | Result
1. Value and cost entered for this month | OK
2. Accruals carried from an earlier month | 1 old accrual(s) carried 2+ months: chase or release.
3. Recognition overridden without a reason | OK
4. Cost to complete is just budget less cost to date | Sub-subcontract.
5. Negative cost to complete | OK
6. Big margin move, or well above tender | Forecast margin moved -9.17 pp.
7. Main contractor valuing below our application, three months running | OK

## CVR J103
J103 Mill Lane offices fit-out: September 2026
| This month | Last month | Movement
Internal valuation | 69000 | 30500 | 38500
Forecast final value | 152000 | 145000 | 7000
Forecast final cost | 124750 | 123250 | 1500
Forecast margin | 27250 | 21750 | 5500
Why the margin moved | £
Forecast final measure | 5000
Recognised change | 2000
Deductions / contras | 0
Own labour | 0
Labour-only subs | 0
Materials | -1500
Plant & access | 0
Sub-subcontract | 0
Site overheads | 0
Check | Result
1. Value and cost entered for this month | OK
2. Accruals carried from an earlier month | OK
3. Recognition overridden without a reason | No reason given for VO-03.
4. Cost to complete is just budget less cost to date | Own labour, Labour-only subs, Plant & access, Sub-subcontract, Site overheads.
5. Negative cost to complete | OK
6. Big margin move, or well above tender | Forecast margin moved +2.93 pp.
7. Main contractor valuing below our application, three months running | OK

## Settings
Company name | Northgate Interiors Ltd
1
3
2
0.05
1000
1 | Jun-26 | 2026-06-30 | Own labour | 1 | Certified
2 | Jul-26 | 2026-07-31 | Labour-only subs | 0.9 | Agreed
3 | Aug-26 | 2026-08-31 | Materials | 0.7 | Instructed, value not agreed
4 | Sep-26 | 2026-09-30 | Plant & access | 0.2 | Submitted
|  |  | Sub-subcontract | 0 | Claim
|  |  | Site overheads | 0 | Rejected

## Jobs
Job no. | Job name | Main contractor | Order value | Tender margin % | Retention % | Labour share (for CIS) | CIS rate | Status | Budget: Own labour | Budget: Labour-only subs | Budget: Materials | Budget: Plant & access | Budget: Sub-subcontract | Budget: Site overheads
J101 | Station Road flats | Hallam Build Ltd | 480000 | 0.14 | 0.05 | 0.45 | 0.2 | Live | 150000 | 90000 | 120000 | 22800 | 15000 | 15000
J102 | Riverside school extension | Calder Construction Ltd | 260000 | 0.12 | 0.03 | 0.5 | 0.2 | Live | 90000 | 50000 | 60000 | 12800 | 8000 | 8000
J103 | Mill Lane offices fit-out | Pennine Interiors Ltd | 145000 | 0.15 | 0.05 | 0.4 | 0.2 | Live | 40000 | 25000 | 40000 | 7250 | 5000 | 6000

## Value
Job no. | Period | Period index | Our application (applied) | MC gross valuation | Paid to date (gross of CIS) | Internal measure | Materials on site | Deductions accepted | Deductions disputed | Disputed: % you expect to recover | Forecast final measure (blank = order value)
J101 | Jun-26 |  | 98000 | 92000 | 70000 | 90000 | 5000 | 0 | 0 | 0
J101 | Jul-26 |  | 162000 | 152000 | 125000 | 150000 | 7000 | 0 | 0 | 0
J101 | Aug-26 |  | 233500 | 216000 | 180000 | 209000 | 6000 | 0 | 0 | 0
J101 | Sep-26 |  | 295800 | 270400 | 205200 | 261000 | 4000 | 1200 | 3000 | 0
J102 | Jun-26 |  | 40000 | 39000 | 30000 | 38000 | 2000 | 0 | 0 | 0
J102 | Jul-26 |  | 82000 | 80000 | 62000 | 79000 | 3000 | 0 | 0 | 0
J102 | Aug-26 |  | 128000 | 124000 | 100000 | 122000 | 2500 | 0 | 0 | 0
J102 | Sep-26 |  | 171000 | 165000 | 128000 | 162000 | 3000 | 2500 | 0 | 0
J103 | Aug-26 |  | 30000 | 29500 | 0 | 29000 | 1500 | 0 | 0 | 0
J103 | Sep-26 |  | 68000 | 66000 | 28000 | 65000 | 2000 | 0 | 0 | 0 | 150000

## Cost & Forecast
Job no. | Period | Period index | Cost head | Ledger cost to date | Cost to complete (CTC) | CTC basis | Comment
J101 | Jun-26 |  | Labour-only subs | 18000 | 72000 | Order +/- variations
J101 | Jun-26 |  | Materials | 26000 | 94000 | Remeasure x current rates
J101 | Jun-26 |  | Own labour | 32000 | 118000 | Days x rate
J101 | Jun-26 |  | Plant & access | 6000 | 16800 | Time-related
J101 | Jun-26 |  | Site overheads | 4200 | 10800 | Time-related
J101 | Jun-26 |  | Sub-subcontract | 0 | 15000 | Order +/- variations
J101 | Jul-26 |  | Labour-only subs | 33000 | 58000 | Order +/- variations
J101 | Jul-26 |  | Materials | 44000 | 76000 | Remeasure x current rates
J101 | Jul-26 |  | Own labour | 56000 | 95000 | Days x rate
J101 | Jul-26 |  | Plant & access | 9500 | 13300 | Time-related
J101 | Jul-26 |  | Site overheads | 6800 | 8200 | Time-related
J101 | Jul-26 |  | Sub-subcontract | 3000 | 12000 | Order +/- variations
J101 | Aug-26 |  | Labour-only subs | 46500 | 45000 | Order +/- variations
J101 | Aug-26 |  | Materials | 41000 | 79000 | Remeasure x current rates
J101 | Aug-26 |  | Own labour | 78000 | 74000 | Days x rate
J101 | Aug-26 |  | Plant & access | 11200 | 11600 | Time-related
J101 | Aug-26 |  | Site overheads | 7000 | 2650 | Time-related
J101 | Aug-26 |  | Sub-subcontract | 4000 | 11000 | Order +/- variations
J101 | Sep-26 |  | Labour-only subs | 58650 | 33500 | Order +/- variations
J101 | Sep-26 |  | Materials | 52000 | 61000 | Remeasure x current rates
J101 | Sep-26 |  | Own labour | 99595 | 56000 | Days x rate
J101 | Sep-26 |  | Plant & access | 13405 | 9395 | Time-related
J101 | Sep-26 |  | Site overheads | 8200 | 7550 | Time-related
J101 | Sep-26 |  | Sub-subcontract | 7400 | 7800 | Order +/- variations
J102 | Jun-26 |  | Labour-only subs | 7000 | 43000 | Order +/- variations
J102 | Jun-26 |  | Materials | 9000 | 51000 | Remeasure x current rates
J102 | Jun-26 |  | Own labour | 14000 | 76000 | Days x rate
J102 | Jun-26 |  | Plant & access | 2500 | 10300 | Time-related
J102 | Jun-26 |  | Site overheads | 1500 | 6500 | Time-related
J102 | Jun-26 |  | Sub-subcontract | 0 | 8000 | Order +/- variations
J102 | Jul-26 |  | Labour-only subs | 16000 | 36000 | Order +/- variations
J102 | Jul-26 |  | Materials | 19000 | 43000 | Remeasure x current rates
J102 | Jul-26 |  | Own labour | 32000 | 62000 | Days x rate
J102 | Jul-26 |  | Plant & access | 4500 | 8300 | Time-related
J102 | Jul-26 |  | Site overheads | 3000 | 5000 | Time-related
J102 | Jul-26 |  | Sub-subcontract | 1000 | 7000 | Order +/- variations
J102 | Aug-26 |  | Labour-only subs | 26000 | 31000 | Order +/- variations
J102 | Aug-26 |  | Materials | 30000 | 36000 | Remeasure x current rates
J102 | Aug-26 |  | Own labour | 52000 | 52000 | Days x rate
J102 | Aug-26 |  | Plant & access | 6800 | 6500 | Time-related
J102 | Aug-26 |  | Site overheads | 4200 | 4300 | Time-related
J102 | Aug-26 |  | Sub-subcontract | 2000 | 6000 | Order +/- variations
J102 | Sep-26 |  | Labour-only subs | 37000 | 25000 | Order +/- variations
J102 | Sep-26 |  | Materials | 41000 | 26000 | Remeasure x current rates
J102 | Sep-26 |  | Own labour | 74000 | 44000 | Days x rate
J102 | Sep-26 |  | Plant & access | 9000 | 4300 | Budget less cost (avoid)
J102 | Sep-26 |  | Site overheads | 5600 | 2800 | Time-related
J102 | Sep-26 |  | Sub-subcontract | 3500 | 4500 | Order +/- variations
J103 | Aug-26 |  | Labour-only subs | 5000 | 20000 | Order +/- variations
J103 | Aug-26 |  | Materials | 9000 | 31000 | Remeasure x current rates
J103 | Aug-26 |  | Own labour | 8000 | 32000 | Days x rate
J103 | Aug-26 |  | Plant & access | 1500 | 5750 | Time-related
J103 | Aug-26 |  | Site overheads | 1200 | 4800 | Time-related
J103 | Aug-26 |  | Sub-subcontract | 0 | 5000 | Order +/- variations
J103 | Sep-26 |  | Labour-only subs | 10500 | 14500 | Order +/- variations
J103 | Sep-26 |  | Materials | 19000 | 21000 | Remeasure x current rates
J103 | Sep-26 |  | Own labour | 17000 | 23000 | Days x rate
J103 | Sep-26 |  | Plant & access | 2800 | 4450 | Time-related
J103 | Sep-26 |  | Site overheads | 2400 | 3600 | Time-related
J103 | Sep-26 |  | Sub-subcontract | 1500 | 3500 | Order +/- variations

## Accruals
Job no. | Cost head | Supplier / source | Reason | Ref | Amount | First period | Counts through period | First index | Through index | Why still not invoiced?
J101 | Materials | Gypframe Supplies | Delivery not invoiced | DN 44120 | 6400 | Aug-26 | Aug-26
J101 | Plant & access | Hi-Reach Hire | Plant hire not invoiced | HR-2291 | 2000 | Aug-26 | Sep-26 |  |  | Still not invoiced: hire company's September billing run is late
J101 | Own labour | Payroll | Labour timesheet | Wk 35 | 3000 | Aug-26 | Aug-26
J101 | Materials | Gypframe Supplies | Delivery not invoiced | DN 45002 | 5400 | Sep-26 | Sep-26
J101 | Labour-only subs | K Walsh Drylining | Labour-only / sub-sub liability | Wk 39 | 3000 | Sep-26 | Sep-26
J102 | Materials | British Board Co | Delivery not invoiced | DN 8812 | 2200 | Jul-26 | Sep-26 |  |  | Disputed delivery; supplier credit expected
J102 | Own labour | Payroll | Labour timesheet | Wk 39 | 1800 | Sep-26 | Sep-26
J103 | Materials | Gypframe Supplies | Delivery not invoiced | DN 45120 | 1500 | Sep-26 | Sep-26

## Change
Ref | Job no. | Period | Period index | Description | Type | Status | Claimed | MC certified on this item | Agreed value | Override % | Override reason
VO-01 | J101 | Jul-26 |  | Extra fire-line boarding to stair cores | MC instruction | Submitted | 12000 | 0
VO-01 | J101 | Aug-26 |  | Extra fire-line boarding to stair cores | MC instruction | Instructed, value not agreed | 12000 | 0
VO-01 | J101 | Sep-26 |  | Extra fire-line boarding to stair cores | MC instruction | Agreed | 12000 | 0 | 11500
DW-01 | J101 | Aug-26 |  | Making good after M&E (daywork sheets 14-19) | Daywork sheet | Submitted | 3000 | 0
DW-01 | J101 | Sep-26 |  | Making good after M&E (daywork sheets 14-19) | Daywork sheet | Certified | 3000 | 2600
CL-01 | J101 | Sep-26 |  | Disruption: late access to level 3 | Our claim | Claim | 9500 | 0
VO-02 | J102 | Aug-26 |  | Acoustic upgrade to music room | MC instruction | Instructed, value not agreed | 8000 | 0
VO-02 | J102 | Sep-26 |  | Acoustic upgrade to music room | MC instruction | Instructed, value not agreed | 8000 | 0
VO-03 | J103 | Sep-26 |  | Additional bulkheads, level 2 | MC instruction | Submitted | 4000 | 0 |  | 0.5